## Cover Page
Project Scope
Detailed Bugs Report for Functional Test for JoPACC (JOIN Start-ups) [WO 27] Vesta Mobile Application Round (1) |  | Audit Trail |  |  |  |  | Component Name | Component ID
|  | Version | Date |  | Comment |  | Vesta Mobile App | S01
|  | V 82.03.[27].110 | 28/01/2026 |  | QA - Round 1
Test Execution Dates
|  | Round |  | Actual Dates |  | Notes
|  | Round 1 |  | 21-01-2026 to 27-01-2026 |  | Round 1 - Functional Execution Test
Used Test basis
Vesta Mobile App Demo
Prepared by: National Software Quality Assurance Centre Royal Scientific Society | Prepared for: Jordan Payments and Clearing Company (JoPACC) Amman, Jordan
Date of submission: 28-01-2026 | Version no: V 82.03.[27].110

## Bugs Report
Test Round | Test Type | Bug ID | Issue Description | Issue Steps | Expected Result | Actual Result | Test Data | Severity | Evidence Name | Component | Vendor Note | Round 2 - Retest Result | Round 2 - RSS Note | Round 2 - Test Data | Round 2 - Severity | Round 2 - Evidence Name
Round 1 | Functional Testing | VEST527-2 | The validity duration is not shown in SMS messages or within the application interface. | 1-Open Join us screen 2-Enter the required data and continue 3-Enter valid phone number and note the SMS and the application page | The OTP SMS message should clearly indicate the validity duration of the OTP (e.g., This OTP is valid for 5 minutes). | 1-The OTP SMS message does not include details about the OTP validity period. 2-The application screen does not display the OTP expiration duration or the remaining time. | - | High | VEST527-2-R1 | S01
Round 1 | Functional Testing | VEST527-3 | Phone number is blocked after three failed attempts or OTP requests for an undefined duration for the user | 1-Open Join us screen 2-Enter the required data and continue 3-Enter valid phone number and request for otp 3 times without entering the value and note the result 4-enter otp 3 times with wrong value and note the result | 1-The block duration should be clearly defined. 2-The user should be informed about the block duration and the steps required to regain access. 3-Based on the email received from Mr. Ahmed dated 22/1/2026, the phone number block duration should not exceed 30 minutes. | 1-The phone number is blocked after three failed OTP attempts or three OTP requests. 2-No information is provided to the user regarding the block duration or recovery process. 3-Currently, the application blocks the phone number for several hours, which is much longer than the specified limit. | - | High | VEST527-3-R1 | S01
Round 1 | Functional Testing | VEST527-4 | User can request a new OTP immediately without 60-second countdown as defined in requirements | 1-Open Join us screen 2-Enter the required data and continue 3-Enter valid phone number and request for otp and note the resend otp feature | 1-The user should not be able to request a new OTP until the 60-second cooldown period has elapsed. 2-A visible 60-second countdown timer should be displayed to inform the user when a new OTP can be requested, in accordance with the requirements document. | 1-The user can request a new OTP immediately after the first request. 2-No 60-second countdown timer is displayed on the application. | - | High | VEST527-4-R1 | S01
Round 1 | Functional Testing | VEST527-5 | Password requirements are only displayed at the final step of OTP verification as error message. | 1-Open Join us screen 2-Enter the required data and enter the password with value (111) and continue 3-Enter valid phone number and request for otp and note the result | Password requirements should be clearly presented at the start of the registration process, informing users of the rules before they enter or submit a password and proceed to the next step. | 1-Password requirements/hints are displayed only as an error message on the final tab during the OTP verification step. 2-No advance indication of the password rules is provided earlier in the registration process. | - | High | VEST527-5-R1 | S01
Round 1 | Functional Testing | VEST527-6 | Application does not handle logout properly from profile page | 1-Log in to the application 2-navigate to profile page 3-click on Logout button and notice the current and other pages in the app | When the user logs out from the Profile page, the application should terminate the session and redirect the user to the login screen. | Logging out from the “My Profile” page does not terminate the session correctly and the user remains logged in, and the displayed personal information disappears and replaced with information of an unknown user. | User name: Nidaa Password: Nidaaa111 | Medium | VEST527-6-R1 | S01
Round 1 | Functional Testing | VEST527-7 | Settings page displays blank when opened from sidebar menu | 1-Log in to the application 2-navigate to settings from the Sidebar Menu and notice the result | Selecting settings from the sidebar menu should display the complete settings page with all configurable options visible and accessible. | The Settings page displays as blank with no content or options when accessed via the sidebar menu. | User name: Nidaa Password: Nidaaa111 | High | VEST527-7-R1 | S01
Round 1 | Functional Testing | VEST527-8 | Application does not support arabic language | 1-Log in to the application 2-navigate to settings from the Sidebar Menu and try to change the language and note the result | The application should support both English and Arabic languages to ensure accessibility for all users | The application is only available in English | User name: Nidaa Password: Nidaaa111 | Medium | VEST527-8-R1 | S01
Round 1 | Functional Testing | VEST527-9 | Date picker icon is not functional | 1-Log in to the application 2-navigate to Sidebar Menu and try to change the day of month from date picker icon and note the result | The date icon should be functional, enabling the user to select a specific day directly, while restricting the selectable days based on the correct number of days in each month for accurate date selection. | The date icon is displayed but cannot be clicked reducing usability and efficiency | User name: Nidaa Password: Nidaaa111 | Low | VEST527-9-R1 | S01
Round 1 | Functional Testing | VEST527-10 | Application Does Not Provide Change Password or Forgot Password Functionality | 1-Navigate to the Log in page in the application and try to reset or forget password and note the result | 1-Users should be able to change their password from the application settings or profile section. 2-A Forgot Password option should be available on the login screen to allow users to reset their password securely. | 1-No option is available to change the password within the application. 2-The application does not provide a Forgot Password or password recovery functionality. | - | High | VEST527-10-R1 | S01
Round 1 | Functional Testing | VEST527-11 | Button design inconsistency and misaligned text on app permissions screen | 1-Log in to the application 2-navigate to my accounts and try to add bank account and note the Permissions Screen | 1-All buttons on the permissions screen should follow a consistent design 2-Text inside buttons should be properly aligned (centered). | 1-Buttons appear with inconsistent designs. 2-The text inside the buttons is misaligned, making the UI appear inconsistent and unprofessional. | User name: Nidaa Password: Nidaaa111 | Low | VEST527-11-R1 | S01
Round 1 | Functional Testing | VEST527-12 | Incorrect redirection when selecting (No, cancel) on app permissions confirmation screen | 1-Log in to the application 2-navigate to my accounts and try to add bank account 3-choose No, cancel in Permissions Screen and note the result | 1-When the user selects (No, cancel) on the permissions confirmation screen, the application should redirect the user back to the bank selection page. 2-The user should be able to choose a different bank or cancel the process. | Selecting (No, cancel) redirects the user directly to the bank login page instead of the bank selection page. | User name: Nidaa Password: Nidaaa111 | Medium | VEST527-12-R1.A VEST527-12-R1.B | S01
Round 1 | Functional Testing | VEST527-13 | Incorrect user flow between bank login, permissions, and add accounts pages | 1-Log in to the application 2-navigate to my accounts and try to add bank account 3-choose allow & continue in Permissions Screen and note the result | 1-User is redirected to the bank login page. 2-After successful bank authentication, the user is taken to the application permissions approval screen. 3-Upon approving the permissions, the user is redirected directly to the Add Accounts page. | 1-User is redirected to the permissions approval screen without logging in to the bank. 2-After approving the permissions, the user is redirected to the Add Accounts page. 3-The bank login step is skipped. | User name: Nidaa Password: Nidaaa111 | High | VEST527-13-R1.A VEST527-13-R1.B | S01
Round 1 | Functional Testing | VEST527-14 | Bank account linking functionality is not working | 1-Log in to the application 2-navigate to my accounts and add bank account 3-exit and re-enter the accounts page and note the result 4-note the data in the home screen | 1-Users should be able to link bank accounts successfully. 2-Linked accounts should remain visible and accessible and linked after exiting and re-entering the accounts page. 3-Exiting the accounts page without performing any action should not clear existing account data or balances. 4-The application should retain all linked account information until the user explicitly removes an account. | 1-Linked accounts disappear after exiting and re-entering the accounts page. 2-Exiting the accounts page without interaction clears the balance data on the home page. 3-The application appears empty, with no linked accounts or data. | User name: Nidaa Password: Nidaaa111 | High | VEST527-14-R1 | S01
Round 1 | Functional Testing | VEST527-15 | IBAN is not Masked in vesta app | 1-Log in to the application 2-navigate to my accounts and try to add bank account 3-choose allow & continue in Permissions Screen and add account and note the account identifier in vesta app | The IBAN should be partially masked (e.g., showing only the last 4 digits) to protect sensitive user information. | 1-The IBAN is displayed in full without any masking. 2-Sensitive information is exposed to anyone viewing the screen. | User name: Nidaa Password: Nidaaa111 | High | VEST527-15-R1 | S01
Round 1 | Functional Testing | VEST527-16 | New added transactions not reflected in total expense on home page | 1-Log in to the application 2-navigate to add transaction 3-add debit transaction and note the result | 1-Newly debit entered transactions should be reflected immediately in the Total Expense section on the home page. 2-Users should be able to view updated total expenses without needing to navigate away from the home page. | 1-Total Expense on the home page is not updated immediately after entering new debit transactions. 2-The values only update after entering and exiting the Spendings page. | User name: Nidaa Password: Nidaaa111 | Medium | VEST527-16-R1 | S01
Round 1 | Functional Testing | VEST527-17 | Masked Account Label Name Inconsistency Between Manual Entry and Bank Sync | 1-Log in to the application 2-navigate to add transaction 3-add transaction and note the name of Masked Account Label 4- open Bank Sync transaction and note the name of Masked Account Label | The masked account label name should be consistent, whether the account is added manually or retrieved via bank syncing. | The masked account label name added manually display a different masked label name than those retrieved via bank syncing. | User name: Nidaa Password: Nidaaa111 | Medium | VEST527-17-R1 | S01
Round 1 | Functional Testing | VEST527-18 | Application allows adding transactions with future dates | 1-Log in to the application 2-navigate to add transaction 3-add transaction in future date and note the result | The application should prevent users from selecting a future date when adding a transaction | Users are able to select a future date and save the transaction successfully | User name: Nidaa Password: Nidaaa111 | Medium | VEST527-18-R1.A VEST527-18-R1.B | S01
Round 1 | Functional Testing | VEST527-19 | Incorrect bank SMS transaction parsing and acceptance of invalid bank messages | 1-Log in to the application 2-navigate to add transaction 3-add transaction (credit, debit, wrong SMS format(only letters or numbers)) paste from bank SMS and note the result | 1-The application should correctly identify the transaction type (deposit or withdrawal). 2-Merchant details should be extracted accurately. 3-Invalid SMS messages should trigger an error message and prevent saving the transaction. | 1-Transactions are not classified (deposit/withdrawal). 2-Merchant field information is incorrect. 3-Invalid messages are accepted without validation, causing wrong data in the app. | User name: Nidaa Password: Nidaaa111 | Medium | VEST527-19-R1 | S01
Round 1 | Functional Testing | VEST527-20 | The "Frequency" field is not displayed for upcoming payments in the Personal Budget section. | 1-Log in to the application 2-navigate to personal budget 3-note the upcoming payments section fields | 1-The Upcoming Payments section should display the Frequency of each scheduled payment (e.g., daily, weekly, monthly). 2-Users should be able to identify the recurrence pattern of upcoming payments easily. | The Frequency field is not displayed, contrary to the requirements document. | User name: Nidaa Password: Nidaaa111 | Medium | VEST527-20-R1 | S01
Round 1 | Functional Testing | VEST527-21 | Application Prevents Entering Total Income as Zero | 1-Log in to the application 2-navigate to total income and set as Zero and note the result | 1-The application should allow users to enter 0 as the total income. 2-The app should handle this case correctly without validation errors, as it is a valid budgeting scenario. | 1-The application prevents entering 0 as the total income value. 2-Users are unable to proceed when their total income is zero. | User name: Nidaa Password: Nidaaa111 | Medium | VEST527-21-R1 | S01
Round 1 | Functional Testing | VEST527-22 | Button Misalignment When Entering an Invalid Monthly Income Value | 1-Log in to the application 2-navigate to total income and try to set as Zero and note the buttons | The buttons should remain properly aligned regardless of validation errors | Entering a rejected value in the monthly income field causes the buttons to become misaligned. | User name: Nidaa Password: Nidaaa111 | Low | VEST527-22-R1 | S01
Round 1 | Functional Testing | VEST527-23 | Spending budget bar is not implemented correctly and does not open detailed view | 1-Log in to the application and navigate to spending analysis 2- note the budget bar | Tapping the bar or the arrow icon should expand it and display a detailed spending bar, as specified in the requirements. | 1-The Spending Budget Bar does not respond to user interaction. 2-Clicking the arrow icon does not expand the bar or display any detailed visualization. | User name: Nidaa Password: Nidaaa111 | High | VEST527-23-R1.A VEST527-23-R1.B | S01
Round 1 | Functional Testing | VEST527-24 | Time period filters are missing in the application | 1-Log in to the application and navigate to spending analysis 2-try to search via Time Period Filters and note the result | Time Period Filters should be visible and accessible within the application as mentioned in the requirement. | Time Period Filters are completely missing from the application | User name: Nidaa Password: Nidaaa111 | High | VEST527-24-R1 | S01
Round 1 | Functional Testing | VEST527-25 | User cannot manually update total savings amount | 1-Log in to the application and navigate to savings goals 2-try to manually update Total savings amount and note the result | The user should be able to manually edit or update the total savings amount as mentioned in the documentation. | The total savings value cannot be modified by the user. | User name: Nidaa Password: Nidaaa111 | High | VEST527-25-R1.A VEST527-25-R1.B | S01
Round 1 | Functional Testing | VEST527-26 | The error message is displayed on the wrong screen. | 1-Log in to the application and navigate to savings goals 2-try to deallocate amount grater than the amount available in current in goal amount and note the result | The error message should be displayed immediately and clearly on the same screen where the error occurs. | The error message behavior is inconsistent: it does not appear on the correct screen when clicking Allocate, and appears on the outer screen when clicking Delete. | User name: Nidaa Password: Nidaaa111 | Medium | VEST527-26-R1.A VEST527-26-R1.B | S01
Round 1 | Functional Testing | VEST527-27 | Remaining amount appears as negative value in savings goal card | 1-Log in to the application and navigate to savings goals 2-try to allocate amount grater than the goal amount and note the result | The remaining amount should always display a positive value when you allocate new amount and the goal is fully reached. | The remaining amount in the Savings Goal card appears as a negative value, even though the goal exceeded. | User name: Nidaa Password: Nidaaa111 | Medium | VEST527-27-R1.A VEST527-27-R1.B | S01
Round 1 | Functional Testing | VEST527-28 | Unclear error message displayed to the user when create new household | 1-Log in to the application and navigate to household 2-try to create new household and note the result | Error messages should be clear, concise, and user-friendly | 1-The error message is unclear and ambiguous. 2-The error message does not consistently appear when attempting to add all households. It appears sometimes but not always 3-The household is successfully created after the error message appears , which is misleading and inconsistent. | User name: Nidaa Password: Nidaaa111 | Medium | VEST527-28-R1 | S01
Round 1 | Functional Testing | VEST527-29 | Member count not displayed on household card | 1-Log in to the application and navigate to household 2- create new household and note the household card | The household card should display the Member Count clearly | Users cannot see the number of members directly from the card, contrary to the requirements. | User name: Nidaa Password: Nidaaa111 | Medium | VEST527-29-R1.A VEST527-29-R1.B | S01
Round 1 | Functional Testing | VEST527-30 | Household name is not editable | 1-Log in to the application and navigate to household 2- create new household and open it and try to change the name and note the result | Users should be able to edit the household name directly from the household card or details screen. | Users are unable to update household names, contrary to the requirements. | User name: Nidaa Password: Nidaaa111 | Medium | VEST527-30-R1.A VEST527-30-R1.B | S01
Round 1 | Functional Testing | VEST527-31 | Updated transaction category does not persist after reopening in the household | 1-Log in to the application and navigate to household 2- Update transaction category and close-reopen the household and note the result | When a transaction category is updated, the change should be persisted in the app | A success confirmation message is displayed, but the updated category is not saved | User name: Nidaa Password: Nidaaa111 | High | VEST527-31-R1 | S01
Round 1 | Functional Testing | VEST527-32 | New added transaction doesn't appear in spending categories in the household | 1-Log in to the application and navigate to household 2- add a new transaction category and note the household spending categories | when New transaction added it should appear in spending categories in the household | New added transaction doesn't appear in spending categories in the household | User name: Nidaa Password: Nidaaa111 | High | VEST527-32-R1 | S01
Round 1 | Functional Testing | VEST527-33 | Deleted transaction stills appear in house hold latest transaction | 1-Log in to the application and navigate to household 2- delete a transaction and note the household latest transaction | Deleted transaction should disappear from house hold latest transaction | Deleted transaction stills appear in house hold latest transaction | User name: Nidaa Password: Nidaaa111 | High | VEST527-33-R1 | S01
Round 1 | Functional Testing | VEST527-34 | Invite deep link does not open when app is already logged in | 1-Open a shared invitation with an already logged in user and note the result | Invite deep link should open when app is already logged in | Invite deep link does not open when app is already logged in | User name: majd Password: abc_123 | High | VEST527-34-R1 | S01